## Sheet1
|  |  | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | March | Apr
|  |  | 2018 |  |  |  | 2019 | [11 empty] | 2020
WQ Funding Cycle Process Steps
| Applications Submittal | 8/13 - 10/15 | bar: Sep to Oct
| Application Evaluation, Rating, and Ranking | 10/16 - 12/26 | bar: Oct to Dec
Issue Draft Funding List | bar: Jan
| Public Comment | 1/18/19 - 2/18/19 | bar: Jan to Feb
| Final Funding List Issued | 2019-06-28 | bar: June
| Agreement Developed | 7/19 - 01/20 | bar: July to Jan
| Project Management (1-5 years) |  | Feb: x; Mar: x; Apr: x; May: x; June: x; July: x; Aug: x; Sep: x; Oct: x; Nov: x; Dec: x; Jan: x; Feb: x; March: x; Apr: x ----->
Task | Description | Due Date
1.1 | Progress Reports that include descriptions of work accomplished, project challenges or changes in the project schedule. Submitted at least quarterly. | 2019-10-31 | bar: Oct; Jan; Apr; July; Oct; Jan
1.2 | Recipient Closeout Report (EAGL Form) | 2021-01-29 | bar: Jan
1.3 | Two-page Outcome Summary Report | 2021-01-29 | bar: Jan
2 | Design Plans and Specs, Environmental Review
2.1 | Complete SEPA determination. Upload copy of SEPA determination documentation to EAGL and notify ECOLOGY upon completion. | 2020-01-03 | bar: Jan
2.2 | Complete DAHP EZ-1 Form or ECOLOGY’s ECY 05-05/106 form. Upload form along with applicable supplemental cultural resources documentation, if available. Notify ECOLOGY. | 2019-10-31 | bar: Oct
2.3 | Develop Inadvertent Discovery Plan, upload to EAGL, and notify ECOLOGY. | 2020-10-31 | bar: Oct
2.4 | Complete a Stormwater Project Design Report. Submit one hard copy to ECOLOGY engineer, along with a digital copy uploaded to EAGL. Notify ECOLOGY. | 2019-07-19 | bar: July
2.5 | Prepare responses to ECOLOGY Stormwater Project Design Report comments. Upload response to EAGL and notify ECOLOGY. | 2019-08-30 | bar: Aug
2.6 | Upload Ecology Design Report Acceptance Letter to EAGL and notify ECOLOGY. | 2019-09-27 | bar: Sep
2.7 | Prepare 90% Design Package to detail the completed final design. Upload to EAGL and notify ECOLOGY. | 2019-10-01 | bar: Oct
2.8 | Prepare responses to ECOLOGY 90 Percent Design Package comments, upload to EAGL, and notify ECOLOGY upon completion. This step may take several exchanges, and may include revisions to the final 90 Percent Design package. Once finalized, a hard copy will also be submitted to the ECOLOGY Project Manager, who will review along with the ECOLOGY Engineer. | 2018-10-31 | bar: Oct
2.9 | Upload Ecology 90 Percent Design Package Acceptance Letter to EAGL and notify ECOLOGY. | 2019-11-29 | bar: Nov
2.1 | Develop a list of permits acquired and environmental review documents. Upload the list to EAGL and notify ECOLOGY. | 2020-03-06 | bar: Mar
2.11 | Prepare Final Bid Package. Upload to EAGL and notify ECOLOGY. | 2020-03-27 | bar: Mar
3 | Construction Management
3.1 | Provide a copy of contract documents (e.g. bid announcement, bid award, and bid tabulations). Upload to EAGL and notify ECOLOGY | 2020-04-30 | bar: Apr
3.2 | Provide a copy of signed and dated construction contract. Upload to EAGL and notify ECOLOGY. | 2020-05-29 | bar: May
3.3 | Develop Construction Quality Assurance Plan. Upload to EAGL and notify ECOLOGY when complete. | 2020-06-30 | bar: June
3.4 | Hold pre-construction conference. Upload meeting notes to EAGL and notify ECOLOGY. | 2020-07-31 | bar: July
3.5 | Update Project Schedule and upload to EAGL using naming convention ‘D3.3 SCHEDULE MO-DA-YEAR. Notify ECOLOGY. | 2020-07-01 | bar: July
3.6 | Revise cash flow estimates when changes in construction schedule occur. Upload to EAGL using naming convention ‘D3.4 CASHFLOW MO-DA-YEAR’. Notify ECOLOGY. | 2020-07-17 | bar: July
3.7 | Upload Change Order(s) to EAGL and notify ECOLOGY. | 2020-08-28 | bar: Aug
3.8 | Develop Facility Operation and Maintenance Plan and upload to EAGL using naming convention ‘D3.6 OANDM MO-DA-YEAR’. Notify ECOLOGY. | 2020-09-18 | bar: Sep
3.9 | Complete Stormwater Construction Completion Form and upload to EAGL. Notify ECOLOGY when complete. | 2020-10-16 | bar: Oct
3.1 | Upload Project Area Shapefile (.zip) or ECOLOGY-approved equivalent for GIS-compatible project area data. | 2020-10-16 | bar: Oct
4 | Project Construction and Monitoring
4.1 | Construction progress reports included in quarterly reports. | 2020-07-31 | bar: July; Oct; Jan
4.2 | Establish temporary construction access and staging area, traffic controls, and construction erosion/water pollution control measures per ECOLOGY-accepted plans and specifications. Photos and any applicable documentation will be included in quarterly construction progress reports. | 2020-09-01 | bar: Sep
4.3 | Place 44 timber frame structures at key locations (per ECOLOGY-approved plans) to stabilize streambanks and adjacent slopes. Photos and any applicable documentation will be included in quarterly construction progress reports. | 2020-10-16 | bar: Sep to Oct
4.4 | Place 39 timber-matrix bed control structures at incised stream reaches (per ECOLOGY-approved plans). Photos and any applicable documentation will be included in quarterly construction progress reports. | 2020-10-16 | bar: Sep to Oct
4.6 | Install streambed cobles and boulders at the 80th ST E culvert to reduce splash erosion and prevent failure during peak-flow events. Photos and any applicable documentation will be included in quarterly construction progress reports. | 2020-10-16 | bar: Sep to Oct
4.7 | Plant native riparian vegetation as needed along project area, up to 4 acres. Photos and any applicable documentation will be included in quarterly construction progress reports. | 2020-10-16 | bar: Oct
4.8 | Monitor project effectiveness throughout project. Monthly field surveys will record: (1) qualitative morphology changes, (2) quantitative measures of bed aggradation and/or sediment volumes in timber structures (3) assessment of riparian planting survival. Submit recorded field data and photographs in quarterly construction progress reports. | 2020-09-01 | bar: Oct to Dec