## ProjectSchedule
HFC End-of-life Management Program Project Schedule
| Last updated: July 12, 2021 | [9 empty] | Completed ahead of schedule | [6 empty] | Completed on time |  |  |  |  | Completed late |  |  |  | Task in progress |  |  |  | Task scheduled |  |  |  | Task overdue
[10 empty] | May |  | June |  |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  |  | October |  |  |  | November |  |  |  | December
| TASK | TASK LEAD | PLANNED START | PLANNED END | EXPECTED DURATION | ACTUAL START | ACTUAL END | ACTUAL DURATION | PROGRESS | 2021-05-17 | 2021-05-24 | 2021-05-31 | 2021-06-07 | 2021-06-14 | 2021-06-21 | 2021-06-28 | 2021-07-05 | 2021-07-12 | 2021-07-19 | 2021-07-26 | 2021-08-02 | 2021-08-09 | 2021-08-16 | 2021-08-26 | 2021-08-30 | 2021-09-06 | 2021-09-13 | 2021-09-20 | 2021-09-27 | 2021-10-04 | 2021-10-11 | 2021-10-18 | 2021-10-25 | 2021-11-01 | 2021-11-08 | 2021-11-15 | 2021-11-22 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 2021-12-27
Project Development
| Develop project plan | Kimberly | 2021-05-17 | 2021-05-21 | 5 | 2021-05-17 | 2021-05-21 | 5 | 100%
| Identify deliverables | Kimberly | 2021-05-17 | 2021-05-21 | 5 | 2021-05-17 | 2021-05-21 | 5 | 100%
| Identify team members | Program Managers | 2021-05-17 | 2021-05-24 | 8 | 2021-05-21 | 2021-05-24 | 4 | 100%
| Develop roles and responsibilities | Kimberly | 2021-05-17 | 2021-06-04 | 19 | 2021-05-17 | 2021-05-24 | 8 | 100%
| Develop preliminary timeline | Kimberly | 2021-05-17 | 2021-05-21 | 5 | 2021-05-17 | 2021-05-21 | 5 | 100%
| Develop and finalize team charter | Kimberly | 2021-05-17 | 2021-06-04 | 19 | 2021-05-17 | 2021-05-24 | 8 | 100%
| Finalize roles and responsibilities | Kimberly | 2021-05-17 | 2021-06-04 | 19 | 2021-05-17 | 2021-05-24 | 8 | 100%
| Finalize overall project plan | Kimberly | 2021-05-17 | 2021-06-04 | 19 | 2021-05-17 | 2021-05-24 | 8 | 100%
| Program Managers meeting | Program Managers | 2021-05-24 | 2021-05-24 | 1 | 2021-05-24 | 2021-05-24 | 1 | 100%
| Monthly Program Managers check-in scheduled | Kimberly | 2021-05-24 | 2021-06-08 | 16 | 2021-05-24 | 2021-06-08 | 16 | 100%
| Establish SharePoint site | Laura W. | 2021-05-24 | 2021-06-15 | 23 | 2021-06-01 | 2021-06-14 | 14 | 100%
| Weekly team planning meeting established | Kimberly | 2021-05-24 | 2021-05-27 | 4 | 2021-05-24 | 2021-06-03 | 11 | 100%
| Coordinate with rulemaking team to finalize scope of recommendations | Kimberly | 2021-05-24 | 2021-06-10 | 18 | 2021-06-07 |  | 0 | 100%
| Tribal consultation/outreach discussion | Kimberly | 2021-06-01 | 2021-06-18 | 18 | 2021-06-16 | 2021-06-16 | 1 | 100%
| Tribal consultation/outreach follow-up | Kimberly | 2021-07-26 | 2021-08-13 | 19 |  |  | 0
Stakeholder Engagement
| Identify known key stakeholders to solicit feedback | Kimberly | 2021-06-03 | 2021-06-15 | 13 | 2021-06-01 |  | 0 | 100%
| Engage in personal communication to invite participation by key stakeholders | Kimberly | 2021-06-07 | 2021-07-21 | 45 | 2021-06-07 |  | 0 | 75%
| Research/identify other new potential stakeholders, including local government | Kimberly | 2021-06-07 | 2021-07-21 | 45 | 2021-06-07 |  | 0 | 80%
| Engage in personal communication to invite participation by new stakeholders | Kimberly | 2021-06-07 | 2021-07-21 | 45 | 2021-06-02 |  | 0 | 80%
| Launch eComments site | Kimberly | 2021-06-07 | 2021-06-10 | 4 | 2021-06-07 | 2021-06-14 | 8 | 100%
| Launch EZView page | Kimberly | 2021-06-08 | 2021-06-14 | 7 | 2021-06-08 | 2021-06-11 | 4 | 100%
| Prepare webinar/eComments announcements | Kimberly | 2021-06-07 | 2021-06-11 | 5 | 2021-06-08 | 2021-06-11 | 4 | 100%
| Develop schedule informational document / Gantt chart for posting on EZView page | Kimberly | 2021-06-14 | 2021-06-25 | 12 | 2021-06-08 |  | 0 | 80%
| Schedule webinars | Kimberly | 2021-06-07 | 2021-06-09 | 3 | 2021-06-08 | 2021-06-08 | 1 | 100%
| Send webinar announcement to listserv | Linda | 2021-06-14 | 2021-06-18 | 5 | 2021-06-08 | 2021-06-11 | 4 | 100%
| Hold Webinar #1 | Kimberly | 2021-06-30 | 2021-06-30 | 1 |  |  | 0 | 100%
| Hold Webinar #2 | Kimberly | 2021-07-09 | 2021-07-09 | 1 |  |  | 0 | 100%
| On-going stakeholder engagement | TBD | 2021-12-01 | 2022-01-10 | 41 | 2021-05-17 | 2021-07-21 |  | 75%
Additional Research
| Review Don't Drip and Drive Program reports for insight on older vehicles | Kimberly | 2021-06-07 | 2021-06-18 | 12 | 2021-06-10 | 2021-06-14 | 5 | 100%
| Research re cost of replacement refrigerants | Abbey | 2021-06-14 | 2021-07-23 | 40 |  |  | 0 | 10%
| Research re cost of switching to replacements, including new or replacement equipment if needed | Abbey | 2021-06-14 | 2021-07-24 | 41 |  |  | 0 | 10%
| Research re cost of recycling old refrigerants and equipment or disposal and why one or the other | Megan | 2021-06-14 | 2021-07-25 | 42 |  |  | 0 | 75%
| Research current market incentives in Washington | Megan | 2021-06-14 | 2021-07-26 | 43 |  |  | 0 | 75%
| Research current market incentives in other jurisdictions | Megan | 2021-06-14 | 2021-07-27 | 44 |  |  | 0 | 75%
| Research funding options and financial assurance applicability | Kimberly | 2021-06-14 | 2021-07-28 | 45 |  |  | 0 | 40%
Policy Decisions
| Brief management about proposed legislative options (may need to be by email) | Kimberly | 2021-07-09 | 2021-07-12 | 4 |  |  | 0
| Get decision on whether project will (1) make recommendations only or (2) develop bill language | Management Team | 2021-07-12 | 2021-07-16 | 5 |  |  | 0
Report
| Begin drafting report and recommendations | Kimberly | 2021-07-06 | 2021-07-23 | 18 |  |  | 0 | 0%
| Summarize stakeholder feedback | Kimberly | 2021-07-16 | 2021-08-02 | 18 |  |  | 0 | 0%
| Begin incorporating stakeholder feedback into draft report | Kimberly | 2021-08-02 | 2021-08-13 | 12 |  |  | 0 | 0%
| Target date for finished first draft | Kimberly | 2021-08-13 | 2021-08-16 | 4 |  |  | 0
| First round of internal review and edits | Peer reviewers | 2021-08-16 | 2021-08-27 | 12 |  |  | 0
| Incorporate edits and prepare review draft | Kimberly | 2021-08-30 | 2021-09-03 | 5 |  |  | 0
| Draft review by Program Managers | Program Managers | 2021-09-07 | 2021-09-17 | 11 |  |  | 0
| Incorporate edits and prepare revised draft | Kimberly | 2021-09-20 | 2021-10-01 | 12 |  |  | 0
| Complete proposed final report and recommendations | Kimberly | 2021-10-01 | 2021-10-01 | 1 |  |  | 0
| Program "fatal flaw only" review | Program reviewers | 2021-10-04 | 2021-10-08 | 5 |  |  | 0
| Submit final draft for Gov Relations review | Kimberly | 2021-10-11 | 2021-10-11 | 1 |  |  | 0
| Government Relation review | GR Staff | 2021-10-11 | 2021-10-29 | 19 |  |  | 0
| Make Government Relations-requested edits | Kimberly | 2021-11-01 | 2021-11-05 | 5 |  |  | 0
| Submit final for Executive review | Kimberly | 2021-11-08 | 2021-11-08 | 1 |  |  | 0
| Executive review | Executive Staff | 2021-11-08 | 2021-11-29 | 22 |  |  | 0
| Make any final edits from Executive review | Kimberly | 2021-11-29 | 2021-11-30 | 2 |  |  | 0
| Submit final report and recommendations (and bill language, if applicable) to Legislature | Kimberly | 2021-12-01 | 2021-12-01 | 1 |  |  | 0

## Sheet1
Activity 1: Project Development
| Develop project plan | Complete | 2021-05-17 | 2021-05-21 | 100%
| Identify deliverables | Complete | 2021-05-17 | 2021-05-21 | 100%
| Identify team members | Complete | 2021-05-24 | 2021-05-21 | 100%
| Develop roles and responsibilities | Complete | 2021-05-17 | 2021-06-04 | 100%
| Develop preliminary timeline | Complete | 2021-05-17 | 2021-05-21 | 100%
| Develop and finalize team charter | Complete | 2021-05-17 | 2021-06-04 | 100%
| Finalize roles and responsibilities | Complete | 2021-05-17 | 2021-06-04 | 100%
| Finalize overall project plan | Complete | 2021-05-17 | 2021-06-04 | 100%
| Program Managers meeting | Complete | 2021-05-24 | 2021-05-24 | 100%
| Monthly Program Managers check-in scheduled | Complete | 2021-05-24 | 2021-06-08 | 100%
| Establish SharePoint site | In Progress | 2021-05-24 | 2021-06-15 | 75%
| Weekly team planning meeting established | Complete | 2021-05-24 | 2021-05-27 | 100%
| Coordinate with rulemaking team to finalize scope of recommendations | In Progress | 2021-05-24 | 2021-06-10 | 50%
| Tribal consultation/outreach discussion | Deferred | 2021-06-01 | 2021-06-15 | 0%
Activity 2: Stakeholder Engagement
| Identify known key stakeholders to solicit feedback | In Progress | 2021-06-03 | 2021-06-15 | 50%
| Engage in personal communication to invite participation by key stakeholders | In Progress | 2021-06-07 | 2021-07-21 | 0%
| Research/identify other new potential stakeholders, including local government | Not Started | 2021-06-07 | 2021-07-21 | 0%
| Engage in personal communication to invite participation by new stakeholders | Not Started | 2021-06-07 | 2021-07-21 | 0%
| Launch eComments site | In Progress | 2021-06-07 | 2021-06-10 | 50%
| Launch EZView page | In Progress | 2021-06-08 | 2021-06-14 | 50%
| Prepare webinar/eComments announcements | In Progress | 2021-06-07 | 2021-06-11 | 50%
| Schedule webinars | Complete | 2021-06-07 | 2021-06-09 | 100%
| Hold Webinar #1 | Not Started | 2021-06-30 | 2021-06-30 | 0%
| Hold Webinar #2 | Not Started | 2021-07-09 | 2021-07-09 | 0%
Activity 3: Additional Research
| Review Don't Drip and Drive Program reports for insight on older vehicles | Not Started | 2021-06-07 | 2021-06-18 | 0%
| Research re cost of replacement refrigerants | Not Started | 2021-06-14 | 2021-06-25 | 0%
| Research re cost of switching to replacements, including new or replacement equipment if needed | Not Started | 2021-06-14 | 2021-06-25 | 0%
| Research re cost of recycling old refrigerants and equipment or disposal and why one or the other | Not Started | 2021-06-14 | 2021-06-25 | 0%
| Research current market incentives in Washington | Not Started | 2021-06-14 | 2021-06-25 | 0%
| Research current market incentives in other jurisdictions | Not Started | 2021-06-14 | 2021-06-25 | 0%
| Research funding options and financial assurance applicability | Not Started | 2021-06-14 | 2021-06-25 | 0%
Activity 4: Policy Decisions
| Brief management about proposed legislative options (may need to be by email) | Not Started | 2021-07-09 | 2021-07-12 | 0%
| Get decision on whether project will (1) make recommendations only or (2) develop bill language | Not Started | 2021-07-12 | 2021-07-16 | 0%
Activity 5: Report
| Begin drafting report and recommendations | Not Started | 2021-07-06 | 2021-07-16 | 0%
| Summarize stakeholder feedback | Not Started | 2021-07-16 | 2021-08-02 | 0%
| Begin incorporating stakeholder feedback into draft report | Not Started | 2021-08-02 | 2021-08-13 | 0%
| Target date for finished first draft | Not Started | 2021-08-13 | 2021-08-16 | 0%
| First round of internal review and edits | Not Started | 2021-08-16 | 2021-08-27 | 0%
| Incorporate edits and prepare review draft | Not Started | 2021-08-30 | 2021-09-03 | 0%
| Draft review by Program Managers | Not Started | 2021-09-07 | 2021-09-17 | 0%
| Incorporate edits and prepare revised draft | Not Started | 2021-09-20 | 2021-10-01 | 0%
| Complete proposed final report and recommendations | Not Started | 2021-10-01 | 2021-10-01 | 0%
| Program "fatal flaw only" review | Not Started | 2021-10-04 | 2021-10-08 | 0%
| Submit final draft for Gov Relations review | Not Started | 2021-10-11 | 2021-10-11 | 0%
| Government Relation review | Not Started | 2021-10-11 | 2021-10-29 | 0%
| Make Government Relations-requested edits | Not Started | 2021-11-01 | 2021-11-05 | 0%
| Submit final for Executive review | Not Started | 2021-11-08 | 2021-11-08 | 0%
| Executive review | Not Started | 2021-11-08 | 2021-11-29 | 0%
| Make any final edits from Executive review | Not Started | 2021-11-29 | 2021-11-30 | 0%
| Submit final report and recommendations (and bill language, if applicable) to Legislature | Not Started | 2021-12-01 | 2021-12-01 | 0%

## About
SIMPLE GANTT CHART by Vertex42.com
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. TimeSheet About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. This hidden text will not print. To remove these instructions from the worksheet, simply delete column A.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.