## Sheet1
CRBFA Project Subcommittee Master Projects Matrix
GOAL: “The purpose of this matrix of projects is to reflect the Chehalis River Basin Flood Authority’s priorities to provide flood relief and protection in the basin”.
A. | Document Overview and Description: This is a list of flood related projects that were extracted from flood planning documents throughout the Chehalis River Basin. This matrix of projects is not prioritized, and is meant to serve as a baseline of projects for potential future funding. Upon approval of this list by the Chehalis River Basin Flood Authority, the goal of the Project Subcommittee will be to add details to each project, including (a.) Description, (b.) Estimated Cost, (c.) Flood Benefit, and (d.) Stage of Readiness.
B. | How to Read This List: The Sources are from where the projects originated. To date, there are 15 sources that were used. Starting from the left, the numbering system is by the type of project. The projects have been sorted into 9 different sections with respect to the "Project Type". Project Types were developed through the Chehalis River Basin Comprehensive Flood Hazard Management Plan; some have been modified by the CRBFA Project Subcommittee. The Project Title and Location were taken directly from the Project Source. The WRIA is the Watershed Resource Inventory Area, as developed by the Washington State Department of Ecology. The Note columns represents actions that were taken on the project by the Project Subcommittee during the course of assembling this matrix. Projects may be grouped under a main heading, i.e. "Retention Projects" or "Levies and Dikes" under Floodplain Protection. In these cases, the project heading is numbered following the project numbering sequence, and the projects under the heading are numbered in Roman Numerals. Projects highlighted in yellow are those that require some follow-up action as described in the notes column(s).
C. | Project Source
1 | CRBFA Project List May 2011.
2 | New Projects Proposed by Flood Authority Jurisdictions (11/22/2010).
3 | Confederated Tribes of the Chehalis Reservation CFHMP (March 17, 2009).
4 | Chehalis River Basin Draft Comprehensive Flood Management Plan (June 2010).
5 | Centralia Comprehensive Flood Management and Natural Hazards Mitigation Plan Annual Progress Report (Updated April 2011).
6 | Thurston County Annual Progress Report - Implementing Flood Hazard Mitigation Initiatives in the Natural Hazards Mitigation Plan (August 11, 2011).
7 | City of Aberdeen Public Works Master Project List (January 2011).
9 | Grays Harbor County Draft Hazard Mitigation Plan 2001.
10 | City of Chehalis - Bob Nacht.
11 | Lewis County Comprehensive Flood Hazard Management Plan.
12 | Grays Harbor County Draft Hazard Mitigation Plan - Lee Napier.
13 | Description of Potential Enhancement Projects in Upper Chehalis Watershed
14 | Chehalis Basin Watershed Management Plan
15 | Chehalis Basin Partnership - Multi-Purpose Water Storage Assessment
FLOODPLAIN PROTECTION
Number | Project Title | Project Description | Structural / Non-Structural | Location | Estimated Cost | Flood Benefit | Stage of Readiness | Source | WRIA | Note | Note | Note 3/31/12
1 | Montesano WWTP protection |  | Structural | Montesano |  |  |  | 1,4 | 22
2 | Wellhead and water treatment protection |  | Structural | Montesano |  |  |  | 1,4 | 22
3 | Remove road embankment fill under Baich Road approach (abandoned) |  | Structural | Chehalis Reservation |  |  |  | 3 | 22 | CTIR Chehalis Tribe Indian Reservation-No assistance from Flood Authority | Project is currently being conducted and is ongoing.
4 | Wilson Creek flooding of highway | A combination of stormdrain piping changes, tide gates, and fill would prevent the water of Wilson Creek (affected by flooding on the Chehalis) from coming onto the state highway. | Structural | Aberdeen - Fleet Street and Wishkah | 150000 | Reduce flooding on highway | Concept Plan - 12 months | 7 | 22 | Jim to check | Received comments from Larry Bledsoe - keep on the list
5 | Tide gates | Most of our tide gates consist of a single tide gate on the river on the outside of the diking system. A redundant system with a tide gate landward of the dike or further inland would be desirable for operation/maintenance and safety. | Structural | Aberdeen - 15 various locations | 540000 | Prevent flooding in event of broken or stuck tide gate at the river | Concept Plan - 18 months | 7 | 22 | Jim to check | Received comments from Larry Bledsoe - keep on the list
6 | Raise portions of Young Street | There are portions of Young Street which are flooded from the Wishkah River every year. Traffic through the area could be maintained if the elevation of several sections of the roadway were raised. | Structural | Aberdeen - Young Street between Lafayette and Mitchell | 276000 | Protects a collector street from frequent flooding | Preliminary survey completed - 6 months | 7 | 22 | Jim to check | Received comments from Larry Bledsoe - keep on the list
7 | Arthur/Randal bank of Wishkah | Filling in the back yard of a few homes in this area would elevate the points where the river floods the adjacent property. | Structural | Aberdeen - West bank of Wishkah River from Randall to Young Streets | 84000 | Prevent River flooding into Randall Street area | Concept plan - 24 months for design and permitting | 7 | 22 | Jim to check | Received comments from Larry Bledsoe - keep on the list
8 | Raise flood gate thresholds | There are three locations on the south side dike that have large swing gates that had elevation established based on the need of meeting the grade of the railroad that existed at the time of design. The railroad is gone; therefore the threshold of the swing gates and the adjacent road approaches can be modified to meet only the needs of roadways. This would allow the elevation to be raised to the 100 year flood elevation so they would only have to closed if flow greater than the 100 year level was expected. This would simplify logistics during a flooding event and manpower could be allocated elsewhere. | Structural | Aberdeen - On Southside Dike between Boone and Custer | 90000 | Provide protection to the base flood elevation without closing swing gates | Concept plan - 6 months | 7 | 22 | Jim to check | Received comments from Larry Bledsoe - keep on the list
9 | Mill Creek overflow dike on Schey | Flooding from Mill Creek (during high river conditions) can cause flood water to flow into Aberdeen. Raising a couple of blocks of Schley Street would create a dike that would prevent the water from flowing from the Mill Creek wetland into Aberdeen | Structural | Aberdeen - South side of Schley Street from West Boulevard to Fordney | 132000 | Prevents flooding on Millcreek from entering Aberdeen | Concept plan - 12 months | 7 | 22 | Jim to check | Received comments from Larry Bledsoe - keep on the list
10 | Mill Creek flooding | Based on observed elevation of the water in the Mill Creek wetland area it is evident that the water level is being kept artificially high by probable beaver dam. The drainage of a large portion of Aberdeen used to gravity flow into this area but now has to be pumped. Removal of the beaver dams in the Mill Creek wetland area should increase the stormwater storage available in the Mill Creek area during high river events. | Structural | Aberdeen - Millcreek wetland from Lomax to Highway 101 | 150000 | Reduce backup flooding from Mill Creek to Cosmopolis and Aberdeen | Needs removal of beaver dams and permitting - 24 months | 7 | 22 | Jim to check | Received comments from Larry Bledsoe - keep on the list
11 | Frye Creek flooding | During combined high river events and high rainfall events the capacity of the Frye Creek pumping system is exceeded and localized flooding occurs. A combination of alternate solutions could be considered, i.e. upgrading the existing pump and tide gate system, relocating a new facility closer to the river, developing upstream stormwater detention. The City has recently completed some improvements to pumping capacity in the area but has not had sufficient time to evaluate the long term effectiveness of the improvements. | Structural | Aberdeen - Frye Creek between Industrial Road and Chehalis River | 1560000 | Reduce flooding from Frye Creek and high water from Harbor | 36 months | 7 | 22 | Jim to check | Received comments from Larry Bledsoe - keep on the list
12 | Sea Level Rise Problem | The impacts of sea level rise on the base flood have not been addressed in establishing the new FEMA maps. The City needs to develop its own strategy as to how it will evaluate and handle this threat. | Structural | Aberdeen - Entire City | $250,000 Concept Study only | Identify long term strategy and project | Should wait until FEMA has completed coastal study and additional five years of data is available | 7 | 22 | Jim to check | Received comments from Larry Bledsoe - keep on the list
13 | Salzer Creek backwater control |  | Structural | On Salzer Creek in Lewis County and Centralia |  |  |  | 1,4,5,11 | 23 | Added "Centralia" per Emil Pearson
14 | Regional Transportation Flood Alleviation Project Along I-5 in Lewis County |  | Structural | Lewis County and Centralia |  |  |  | 5,11 | 23 | Remove if project is closed by ACE | Emil Pearson does not want this project removed
15 | USACE Centralia Flood Reduction Project - Retitle |  | Structural | Lewis County and Centralia |  |  |  | 5 | 23 | Emil Pearson wants the USACE removed from title
16 | Complete storm and surface water utility projects at Meridian Heights, Mallard Pond Phase 2, and Evergreen Terrace (scheduled 2009) |  | Structural | Thurston County |  |  |  | 2 | 23 | Greg will check with Mark S. | Mark Swartout - Keep on the list | Mark Swartout - Move to the remove project list – should have seen that before.
17 | Scheuber Road Bypass (under Hwy 6) |  | Structural | City of Chehalis |  |  |  | 10 | 23
18 | Elevate Main Street |  | Structural | City of Chehalis |  |  |  | 10 | 23
19 | Increased stormwater on-site detention and retention |  | Structural | Basin-wide |  |  |  | 1,4 | 22-23 | Remove if project is closed by USACE
20 | Off-Channel Storage (conservation easements) |  | Structural | Basin-wide |  |  |  | 1 | 22-23
21 | Determine cause of water backup over Highway 6 |  | Non-structural | Highway 6 |  |  |  | 1,4 | 22-23 | Moved from Planning
22 | Wynoochee Tracts/Wishkah Road |  | Structural | Grays Harbor County |  |  |  | 9 | 22 | Terry to check
23 | Walker Bottom Area/ Wishkah Road |  | Structural | Grays Harbor County |  |  |  | 9 | 22 | Terry to check
24 | Wishkah Road (Kirsch) | 1). Land acquisition to provide more flood plain storage of two parcels located right along the water. 2). Approximately nine homes would be helped by raising them above the flood plain. 3). Replacement culvert near Kersh’s property would have to be a six foot diameter pipe and approximately 90 feet long and relocating Aberdeen’s transmission water main. 4). Construct a sheet pile wall (dike) 1000 feet long. | Structural | Grays Harbor County | 1). $42,000 2). $30,000 per home or $270,000 total 3). $500,000 4). $1,100,000 | Reduce flooding to the Wishkah Road |  |  |  | Added from Terry Willis
25 | Retention Projects - Includes Mainstem Water Retention and Minor Water Retention |  | Structural | Basin-wide |  |  |  | 1 | 22-23
i | Skookumchuck Dam |  | Structural | Basin-wide |  |  |  | 15 | 22,23 | Remove if project is closed by USACE
ii | Alpha Creek - Newaukum River |  | Structural - Water Storage | Lewis County |  |  |  | 15 |  | Hold for NRCS
iii | Above Hanlon - South Fork Chehalis River |  | Structural - Water Storage | Lewis County |  |  |  | 15 |  | Hold for NRCS
iv | Lake Creek - South Fork Chehalis River |  | Structural - Water Storage | Lewis County |  |  |  | 15 |  | Hold for NRCS
v | Lost Creek - South Fork Chehalis River |  | Structural - Water Storage | Lewis County |  |  |  | 15 |  | Hold for NRCS
vi | Charles Hump - Chehalis River |  | Structural - Water Storage | Lewis County |  |  |  | 15 |  | Hold for NRCS
vii | Little Elk Creek - Elk Creek |  | Structural - Water Storage | Lewis County |  |  |  | 15 |  | Hold for NRCS
viii | Bunker Creek - Deep Creek |  | Structural - Water Storage | Lewis County |  |  |  | 15 |  | Hold for NRCS
ix | Upper Deep Creek - Deep Creek |  | Structural - Water Storage | Lewis County |  |  |  | 15 |  | Hold for NRCS
xx | Mill Creek dam in Cosmopolis |  | Structural | Cosmopolis |  |  |  | 1 | 22 | Comments from Mark White: But I do want to know more about this mill pond in cosmopolis. I know the pond and I’m not sure how this has any impact on flooding or flood mitigation. It is a salmon bearing stream and we do not want to see it dammed again, when I don’t see how it has any impact to reduce flood. Is there a study or something to show its impacts if dammed?
xxi | Wynoochee Dam Modifications |  | Structural |  |  |  |  | 15 | 23 | Terry to check with Lee
xxii | Lewis County PUD Upstream Storage Phase 3 Studies |  | Structural | Basin-wide |  |  |  | Lewis County PUD
26 | Levees and Dikes - Repair, maintenance and potential new construction |  | Structural | Basin-wide |  |  |  | 1 | 22-23
i | Humptulips Dike Road |  | Structural | Grays Harbor County |  |  |  | 9 | 22 | Terry to check
ii | Trail/Dike behind Burger King | The Burger King property is located between the Wishkah and the Heron street bridges. Extreme high water can top the bank and flood the adjacent commercial property. A small dike or elevated walkway along the river would help keep the river in its banks. | Structural | Aberdeen - East bank of Wishkah between Wishkah and Heron | 123000 | Prevents river flooding from entering that section of Aberdeen | Stage of Readiness: | 24 months | 22 | Jim to check | Received comments from Larry Bledsoe - keep on the list
iii | Dike bank of Wishkah north of Hwy. | The northeast area of Aberdeen is partially protected by dike along the Chehalis behind the Wal-Mart/Gateway Plaza mall area; however when extreme conditions exist the water will flood the area from the Wishkah river north of the highway. Raising the local road elevations adjacent the Wishkah River and installing tide gates would create a dike which would reduce flooding frequency. | Structural | Aberdeen - East bank of Wishkah from Kansas Street to Chehalis street | 235000 | Prevents river flooding from entering that section of Aberdeen | Concept Plan - 36 months | 7 | 22 | Jim to check | Received comments from Larry Bledsoe - keep on the list
iv | Market Street Dike | High water from the Wishkah River overtops the river bank in the Market Street area. If half the road and sidewalk were raised it would create a small dike which would not protect from the 100 year event but would greatly reduce the frequency of flooding experienced. | Structural | Aberdeen - Market Street from D Street to 1st Street | 483000 | Prevents flood waters from entering that area of the community | Concept Plan - 24 months | 7 | 22 | Jim to check | Received comments from Larry Bledsoe - keep on the list
v | Overtopping levee on the north end of town |  | Structural | Bucoda - North end | Not determined | Reduces flood levels in town | Need design to detemine precise flood benefits and cost estimates. | 1,4 | 23 | Greg will check with Mark S. - keep on list. Not started due to lack of funds
vi | Adna levee improvement |  | Structural | Adna |  |  |  | 1,4 | 23
vii | Enhance the existing Airport Dike | Project consists of elevating the existing airport levy using both earthen material where the footprint at the base is large enough, and floodwalls constructed generally with pilings atop the existing levy where drainage or rights-of-way occur at the base, to protect the airport operation, the commercial area east of the airport runway and the I-5 freeway from closure during a major flood event on the Chehalis River. Airport road at the south end of the airport property would be elevated several feet and terminate in the West Street overcrossing approach. If/when the West St. overcrossing is modified for reconstruction of the freeway, the terminus of the enhanced levy protection could be modified as well to maintain the protection elevations at the south end. Minor elevation enhancements would be needed on the freeway r/w via either berms or lifts on existing pavement to provide required elevation. The state would need to identify protection measures on the east side of the freeway to prevent backwater from that side, such as concrete barriers or floodwalls or berms on the existing r/w. There is also a way to prevent significant flooding from the east side by raising W. Main Street, but that concept has not been studied. The east side can be protected fairly easily (engineering-wise) from both the north and the south, and/or with lower floodwalls where needed on the freeway r/w if the west side is protected by the levy. The flood elevations that occur at the south end of the project are slightly higher than would be required at the north end. RB Engineering has created a civil plan for the Airport Board showing what elevations would be needed to satisfy certification to the proposed new FEMA floodplain standard. That standard is likely to be revised slightly locally when FEMA determines what the 'existing levy' approach will be in their floodplain mapping process. Allyn Roe at the Airport will have a copy of the civil plan for this project. RB Engineering could probably get you a set also. | Structural | City of Chehalis | Engineers actual cost estimate is being calculated presently - Airport Board has requested that information from RB Engineering. Preliminary estimates are around $2M to $2.5M, and engineers report is expected within a month or so. | Project protects major commercial (economic) area as well as the Airport operations and the Interstate Transportation system (I-5). We would need to calculate the value of the commercial area but it's probably around $100M. Interstate commerce loss was pegged at $4M per day of freeway closure. The airport operation provides helicopter services during flood events if the levy is enhanced. Search and rescue operations would also occur if airport is not flooded. Hydraulic flood models using enhanced airport levy and/or completely filling the airport property inside the levy, including the freeway, show only inches of impact outside the levy. If needed, Chehalis has property that could be used for floodplain mitigation. Actual impact from enhancing the existing levy and raising Airport Rd is minimal, but negative political perception of that much area being protected will need to be scientifically rebuked. | Civil plans are already on the shelf. Construction plans could be developed within a month to six weeks. Permitting could be accomplished in a month or so locally. Unknown how Ecology or the Corps would look at this project. | 10 | 23
viii | Southside Dike (Levee) certification |  | Non-structural | Aberdeen |  |  |  | 7 | 22 | Moved from Floodplain Protection, Then moved back to Floodplain Protection (comments from 3/1 Project Subcommittee meeting) | Received comments from Larry Bledsoe - work is being completed in-house and will be completed within one year
| Satsop Floodplain Restoration | This Satsop River floodplain restoration project consists of approximately 100 ac. of floodplain habitat that is negatively impared by approximately 5200 linear feet of constructed dike and approximately 2500 linear feet of riprapped riverbank. Since May 2001 the Satsop Committee (WDFW, Corps, Grays Harbor County, and local citizens) has met to develop a project approach to meet the needs of both fish and people. As a result the committee has worked with the Corps to develop a Channel Migration Study, Preliminary Restoration Plan and has recently been notified of the Corps approval to fund this project under Section 206 Ecosystem Restoration. Throughout the past 1+ years the Satsop Committee has identified the dike, riprap, ponds, and excessive eroding banks as areas to focus restoration efforts. Beginning Fall 2001 the Corps will begin a study phase that will characterize baseline habitat conditions and identify potential improvements to these conditions through restoration actions. Proposed restoration activities will be analyzed using standard modeling techniques to determine if there are potential adverse affects from the restoration project. Once this phase is complete the Satsop Committee will decide on a restoration concept and design. The project is scheduled to be constructed the summer of 2004. The implementation of this project will restore floodplain functions and re-establish access to off-channel habitat. | Structural | Satsop River Floodplain | 1099800 |  | Study Phase (Planning Phase) Plans and Specifications Construction - Total two years |  |  | Added by Terry Willis/Lee Napier from previous SRF Board Grant. This project did receive SRFB funding and a contract was executed, however WDFW returned the funds to RCO when the match from the Corps didn’t materialize.
REDUCTION OF DAMAGE TO EXISTING STRUCTURES
27 | Protect access to Satsop Development Park |  | Structural | Grays Harbor County |  |  |  | 1,4 | 22
28 | Replace U.S. Highway 12 Black River Bridge |  | Structural |  |  |  |  | 3 | 22 | Terry to check with Mark White
29 | Regrade Main Street | This project will raise Main St. to allow passage of emergency vehicles during flood events. Project #128(xxxii) needs to be included to prevent additional backing up of water. | Structural | Bucoda - Main Street | Not determined |  | Need design to detemine precise flood benefits and cost estimates. | 1,4 | 23 | Greg will check with Mark S. | Mark S. sent to Bucoda mayor. Keep on the list.
30 | Implement a home elevation and buyout program | One example from Aberdeen: There are at least 50 homes that, even if all the proposed flood control measures are implemented, will be in danger of flooding during high water events. The only practical solution for those homes is to elevate them above the base flood elevation. | Structural | Basin-wide - (One example) North Aberdeen from Young Street to Wishkah River and from Market Street to River | 1250000 | Prevents flood damage to select homes | No work has started - 5 years to complete | 1,3,4 | 23-24
31 | Southside Dike (Levee) certification | In order for the current flood protection status of South Aberdeen to be recognized Aberdeen needs to complete a certification process for its Dike even though it was designed and built by the Army Corps of Engineers. This process is ongoing and is being done in-house. It is anticipated to be completed within the year. There may be some dike improvements needed to meet the certification requirements. | Non-structural | Aberdeen - Southside Dike – South Aberdeen | 50000 | Documents effectiveness of existing diking system | Stage of Readiness: In process | 7 | 22 | Moved from Floodplain Protection | Received comments from Larry Bledsoe - work is being completed in-house and will be completed within one year
BANK STABILIZATION
32 | Wynoochee River bank stabilization |  | Structural | Montesano |  |  |  | 1,4 | 22
33 | Mary’s River Lumber bank protection |  | Structural | Montesano |  |  |  | 1,4 | 22 | Terry to check on the name
34 | Chehalis River Bank Restoration near Oakville |  | Structural | Grays Harbor County |  |  |  | 9 | 22
35 | Chehalis River Bank Restoration near Porter |  | Structural | Grays Harbor County |  |  |  | 9 | 22
36 | Satsop River Bank Stabilization near Satsop |  | Structural | Grays Harbor County |  |  |  | 9 | 22
37 | Satsop River Bank Stabilization near Satsop Rivera |  | Structural | Grays Harbor County |  |  |  | 9 | 22
38 | Keys Road Chehalis River Bank at Boat Launch near Satsop River |  | Structural | Grays Harbor County |  |  |  | 9 | 22
39 | Streambank stabilization - Skookumchuck River |  | Structural | Bucoda - Near and within the area of Bucoda | Not determined | This will prevent the Skookumchuck River from moving in its floodplain further into the Town of Bucoda. This area is a meandering zone of the river, which means the river has a tendency to move from its current river bed. | Need design to detemine precise flood benefits and cost estimates. | 1,4 | 23 | Greg will check with Mark S. - keep on list. Not started due to lack of funds | Mark S. sent to Bucoda Mayor - not started due to lack of resources
40 | Install floodplain roughening along left bank of Chehalis River downstream of Sickman-Ford Bridge |  | Structural |  |  |  |  | 3 | 23 | CTIR-No assistance from Flood Authority | Completed
41 | Independence Road bank protection |  | Structural | Lincoln Management Unit |  |  |  | 13 | 24 | Ron to check | Received comments from Bob Johnson - Keep on the list
42 | Skookumchuck River - streambank stabilization |  | Structural | Skookumchuck Management Unit (Skookumchuck River, Scatter Creek) |  |  |  | 13 | 24 | Greg will check with Mark S. | Mark Swartout - Keep on the list
CONVEYANCE CAPACITY
43 | Open migration zone of the Satsop |  | Structural | Satsop River |  |  |  | 1,4 | 22
44 | Dredge Lake Sylvia |  | Structural | Montesano |  |  |  | 1,4 | 22
45 | Open relic channel at Marys River oxbow |  | Structural | Grays Harbor County |  |  |  | 1,4 | 22
46 | Widen Stream channel at MP 8.2 of the South Bank Road. |  | Structural | Grays Harbor County |  |  |  | 12 | 22 | Terry to check with Lee
47 | Realign Dillenbaugh Creek |  | Structural | City of Chehalis/ WSDOT |  |  |  | 10 | 23
48 | Remove push-up levee downstream of Sickman-Ford Bridge |  | Structural |  |  |  |  | 3 | 23 | CTIR-No assistance from Flood Authority | Completed
49 | Beneficial sediment management (dredging) |  | Structural | Basin-wide |  |  |  | 1 | 22-23
PLANNING/IMPLEMENTING AND DATA COLLECTION
50 | Evaluate revisions to FEMA mapping |  | Non-structural | Grays Harbor County |  |  |  | 9 | 22
51 | Assess and evaluate alternative solutions to address flooding between MP 1 and MP 5. |  | Non-structural | Grays Harbor County |  |  |  | 12 | 22
52 | Remap high groundwater areas |  | Non-structural | Thurston County - Salmon Ck. Basin, various locations in North County, and small area by Lake Lawrence | 50000 | Risk MAP will benefit the county by being able to apply NFIP regulations on high-groundwater flood areas | This project is part of the FEMA Risk MAP project currently in progress | 1,4 | 23 | Greg will check with Mark S. | Mark Swartout - Keep on the list | Additional data from Mark Swartout 3/27/12
53 | Berwick Creek Drainage Plan |  | Non-structural | Chehalis and Lewis County |  |  |  | 1,4,11 | 23
54 | China Creek Drainage Plan |  | Non-structural | Lewis County and Centralia |  |  |  | 1,4,5,,11 | 23 | Added source 5 per Emil Pearson
55 | Rochester Stormwater Plan |  | Non-structural | Rochester |  |  |  | 1,4 | 23 | Greg will check with Mark S. | Mark Swartout - Keep on the list | Mark Swartout - Remove from the list
56 | Skookumchuck River scour potential study |  | Non-structural | Skookumchuck River |  |  |  | 1,4 | 23 | Remove if project is closed by ACE
57 | Model effects of removing/modifying the Sickman-Ford Bridge Approach |  | Non-structural | Sickman-Ford Bridge |  |  |  | 1,4 | 23 | Remove - Terry to check with Mark W. | CTIR-No assistance from Flood Authority
58 | Draft a prioritized list of road segments and bridges that should be elevated above the 100-year floodplain and culverts that will fail under flood flow. Upgrade these structures if state or federal monies become available. |  | Non-structural | Thurston County | Undetermined cost to do the modeling effort | Reduce localized flooding and provide life safety benefit | Updated LiDAR has been completed. Now modeling needs to occur. | 6 | 23 | Greg will check with Mark S. | Mark Swartout - Keep on the list | Additional data from Mark Swartout 3/27/12
59 | Remap the floodplains for all rivers, streams, and high groundwater areas and update the Flood Insurance Rate Maps (FIRMs) |  | Non-structural | Thurston County | County’s cost will be determined in the near future. | More accurate mapping of the floodplains and high-ground water areas will reduce flood damage. | FEMA’s Risk MAP Coastal project is underway. Deschutes and Lower Chehalis Risk MAP projects are under negotiations. | 6 | 23 | Greg will check with Mark S. | Mark Swartout - Keep on the list | Additional data from Mark Swartout 3/27/12
60 | Acquire MIKE 11, a three-dimensional hydrological modeling software package and AQUARIUS, a USGS standard stream flow modeling software package. |  | Non-structural | Thurston County | 21000 | Better flood modeling and integration with our groundwater flooding. | Nothing has moved forward on this due to lack of funding. | 6 | 23 | Greg will check with Mark S. | Mark Swartout - Keep on the list | Additional data from Mark Swartout 3/27/12
61 | Develop mapping products to achieve all flood maps and data sets so they can be reused at a later date. |  | Non-structural | Thurston County - Throughout the County’s flood plains | County’s cost will be determined in the near future. | More accurate mapping of the floodplains and high-ground water areas will reduce flood damage. | This project is associated with FEMA Risk MAP projects. | 6 | 23 | Greg will check with Mark S. | Mark Swartout - Keep on the list | Additional data from Mark Swartout 3/27/12
62 | Undertake a study of repetitive public cost losses, this would include residential structures, but also include properties such as livestock, out-buildings and rescue costs not already identified by FEMA |  | Non-structural | Thurston County - Throughout the County’s flood plains | County’s cost will be determined in the near future. | More accurate mapping of the floodplains and high-ground water areas will reduce flood damage. | This project is associated with FEMA Risk MAP projects. | 6 | 23 | Greg will check with Mark S. | Mark Swartout - Keep on the list | Additional data from Mark Swartout 3/27/12
63 | Reevaluate land uses and zoning based upon new floodplain maps. |  | Non-structural | Thurston County - Throughout the County’s flood plains | Not applicable | Reduces potential flood damage. | The County as part of our legal settlement excluded density calculations in the floodplain. The new FIRMs will allow more accurate implementation of this provision and the revised Critical Areas Ordinance. | 6 | 23 | Greg will check with Mark S. | Mark Swartout - Keep on the list | Additional data from Mark Swartout 3/27/12
64 | Work with others to determine the width and conditions of buffers along river and stream shorelines |  | Non-structural | Thurston County - Throughout the County’s flood plains | As part of the SMP update part of the costs will be covered by an Ecology grant. The in-house costs are estimated to be $500,000. Other work supported by the SRFB is determined on a project by project basis. | This will assist in identifying areas for riparian restoration, which will provide a flood benefit by reducing flood debris in adjoining properties. | The lead entities for salmon recovery will work with project proponents to perform this work. Also, this is included in the inventory characterization a requirement of the SMP update. | 6 | 23 | Greg will check with Mark S. | Mark Swartout - Keep on the list | Additional data from Mark Swartout 3/27/12
65 | Draft a Comprehensive Plan policy which encourages the creation and use of wetland mitigation bank. |  | Non-structural | Just the Deschutes watershed and possibly the Nisqually in the future. | Currently utilizing a $1.8 million Ecology grant. | Reduce flooding by restoring wetlands and reducing surface water runoff. | Project underway to develop an in-lieu fee program. A type of mitigation bank that will focus on wetlands. | 6 | 23 | Greg will check with Mark S. | Mark Swartout - Keep on the list | Additional data from Mark Swartout 3/27/12
66 | Prepare a new drainage basin plan in priority areas such a Salmon and Yelm Creeks. |  | Non-structural | Salmon Creek basin | $20,000 in house funding. | This is a high groundwater flooding area and will be able predictive based precipitation predictions | County hydrogeologist will begin working at modeling the Salmon Creek basin late 2012. | 6 | 23 | Greg will check with Mark S. | Mark Swartout - Keep on the list
67 | Channel migration zone mapping and analysis and the extent of high quality riparian habitat |  | Non-structural | Basin-wide |  |  |  | 1,4,11 | 22-23
68 | Survey of river cross-sections |  | Non-structural | Basin-wide |  |  |  | 1,4 | 22-23
69 | Study of woody debris in conjunction with flooding |  | Non-structural | Basin-wide |  |  |  | 1,4 | 22-23
70 | Study of aggregates |  | Non-structural | Basin-wide |  |  |  | 1,4 | 22-23
71 | Study of failed riprap |  | Non-structural | Basin-wide |  |  |  | 1,4 | 22-23
72 | Evaluate how groundwater impacts flooding events |  | Non-structural | Basin-wide |  |  |  | 1,4 | 22-23
73 | Evaluate river channel responses to influx and deposition of sediment in vicinity of the Chehalis Reservation |  | Non-structural | Chehalis Tribe |  |  |  | 2 | 22-23 | Terry to check with Mark White
74 | Conduct a study to determine volume, placement, and potential impacts of flood on failed riprap placed by Thurston County on the Chehalis River bank adjacent to Independence Road |  | Non-structural | Chehalis Tribe |  |  |  | 2 | 22-23 | Terry to check with Mark White
75 | Identify and conduct studies that would need to be accomplished in order to design the proposed mitigation strategies (such as raising Moon Road) |  | Non-structural | Chehalis Tribe |  |  |  | 2 | 22-23 | Terry to check with Mark White
76 | Coordinate with the Flood Authority to develop a dynamic model of the middle basin to assess effects of future basin development on the flood hydrology at the Chehalis Reservation. |  | Non-structural | Chehalis Tribe |  |  |  | 2 | 22-23 | Terry to check with Mark White
EDUCATION AND PUBLIC INFORMATION
77 | Develop a community-wide flood hazard educational outreach program |  | Non-structural | Chehalis Tribe |  |  |  | 2 | 23
78 | Provide educational materials on flood hazard management |  | Non-structural | Basin-wide |  |  |  | 1,3,4 | 22-23
79 | Provide flood proofing guidance to residents |  | Non-structural | Basin-wide |  |  |  | 1,4,9 | 22-23
80 | Agricultural Drainage Removal public information |  | Structural | Basin-wide |  |  |  | 15 | 22,23
81 | Low-Impact Development public information |  | Structural | Basin-wide |  |  |  | 15 | 22,23
82 | Inform the public about how they can best protect habitat on their own land. |  | Non-structural | Basin-wide |  |  |  | 14 | 23,24
EMERGENCY RESPONSE AND PREPARDNESS
83 | Improve gauge system in Grays Harbor County - Example Humptulips USGS Station No. 12039005 | The County may be unable to continue cost sharing in the continued operation of this gage. If this occurs the community would lose their only gage for flood warning predictions. | Structural | Grays Harbor County | $12,000 annually | Life and safety benefit. | System is currently operating. Operation would discontinue without funding. | 1,4 | 22 | Example added by Lee Napier
84 | Construct drinking water reservoir |  | Structural | Montesano |  |  |  | 1,4 | 22 | Greg will check with Vickie | Ken Estes said to remove
85 | Install generator at Grays Harbor Fairgrounds |  | Structural | Grays Harbor Fairgrounds |  |  |  | 1,4 | 22
86 | Develop evacuation plans for communities and residents situated downstream from the Nisqually and Skookumchuck River Dams. |  | Non-structural | The precise locations will be identified after the Risk MAP project is completed | County’s cost will be determined in the future. | Life and safety benefit. | Working on an enhanced notification system for impending floods. Next step is once Risk MAP project is completed and we know the depth grids this will show which roads we need to develop evacuation plans for. | 6 | 23 | Ask Mark S. -Thurston County is waiting for the new FEMA H&H modeling of the two rivers |  | Additional data from Mark Swartout 3/27/12
87 | Add gauge just below the Wynoochee Dam |  | Structural | Grays Harbor County |  |  |  | 2 | 23
88 | Consider adding rain gauges |  | Structural | Grays Harbor County |  |  |  | 2 | 23 | Terry to check
89 | Address loss of power and cell phone coverage |  | Non-structural | Basin-wide |  |  |  | 1,4 | 22-23
90 | Establish critter pads to reduce livestock loss |  | Structural | Basin-wide |  |  |  | 1,4 | 22-23
POTENTIAL FLOOD PROJECTS WITH ECOLOGICAL OPPORTUNITIES
91 | Camp Creek drainage improvements |  | Structural | Grays Harbor County |  |  |  | 1,4 | 22
92 | Main Stem Scheuber Ditch Reconnection and Wetland Creation |  | Structural |  |  |  |  | 15 | 23 | Greg to check | Message from Bob Johnson - no one can locate the origin of these projects
93 | South Fork Chehalis Revegetation and Wetland Creation, RM 0 to 5 |  | Structural |  |  |  |  | 15 | 23 | Greg to check | Message from Bob Johnson - no one can locate the origin of these projects
94 | South Fork Chehalis Reconnections and Wetland Creation, South Fork and Main Stem Chehalis Confluence |  | Structural |  |  |  |  | 15 | 23 | Greg to check | Message from Bob Johnson - no one can locate the origin of these projects
95 | Newaukum Revegetation and Wetland Creation, at Chehalis Confluence |  | Structural |  |  |  |  | 15 | 23 | Greg to check | Message from Bob Johnson - no one can locate the origin of these projects
96 | Newaukum Reconnection and Wetland Creation, Stan Hedwall Park |  | Structural |  |  |  |  | 15 | 23 | Greg to check | Message from Bob Johnson - no one can locate the origin of these projects
97 | North Fork/South Fork Newaukum Confluence Connections and Wetland Creation |  | Structural |  |  |  |  | 15 | 23 | Greg to check | Message from Bob Johnson - no one can locate the origin of these projects
98 | Salzer Creek Revegetation and Wetland Creation, Chehalis Confluence |  | Structural |  |  |  |  | 15 | 23 | Greg to check | Message from Bob Johnson - no one can locate the origin of these projects
99 | Salzer Creek Reconnection and Wetland Creation, Frozen Foods Site |  | Structural |  |  |  |  | 15 | 23 | Greg to check | Message from Bob Johnson - no one can locate the origin of these projects
100 | Salzer Creek Revegetation and Wetland Creation, RM 3.1 |  | Structural |  |  |  |  | 15 | 23 | Greg to check | Message from Bob Johnson - no one can locate the origin of these projects
101 | Salzer Creek Revegetation and Wetland Creation, RM 4.5 |  | Structural |  |  |  |  | 15 | 23 | Greg to check | Message from Bob Johnson - no one can locate the origin of these projects
102 | South Fork Chehalis - Bank regrade, low bench, riparian revegetation |  | Structural | Boistfort Management Unit |  |  |  | 13 | 24
103 | River Miles 66 to 80 - Bank regrade, low bench, riparian revegetation |  | Structural | Chehalis Mainstem Management Unit |  |  |  | 13 | 24
104 | Newaukum River - Bank regrade, low bench, riparian revegetation |  | Structural | Newaukum Management Unit |  |  |  | 13 | 24
105 | Newaukum River/Newaukum Valley Golf Course - In-channel enhancements |  | Structural | Newaukum Management Unit |  |  |  | 13 | 24
106 | North Fork Newaukum - riparian and floodplain restoration |  | Structural | Newaukum Management Unit |  |  |  | 13 | 24
107 | Upstream of River Mile 10 - Potential floodplain enhancement |  | Structural | Skookumchuck Management Unit |  |  |  | 13 | 24
108 | Lower watershed - Reconnect, enhance, restore off-channel, floodplain, wetlands |  | Structural | Skookumchuck Management Unit |  |  |  | 13 | 24
109 | Scatter Creek - Sampson Wetland Enhancement Ph. 1 |  | Structural | Skookumchuck Management Unit |  |  |  | 13 | 24
110 | Protect and restore critical areas |  | Structural | Basin-wide |  |  |  | 1,4 | 22-23
111 | Provide habitat for wildlife and fish |  | Structural | Basin-wide |  |  |  | 1,4 | 22-23
112 | Encourage longer rotations between tree cutting in forests |  | Structural | Basin-wide |  |  |  | 1,4 | 22-23
113 | Encourage improvement of forest management practices |  | Structural | Basin-wide |  |  |  | 1,4 | 22-23
114 | Establish reforested corridors along river and stream shorelines, working with landowners and others |  | Structural | Along all stream and river shorelines in the County | As part of the SMP update part of the costs will be covered by an Ecology grant. The in-house costs are estimated to be $500,000. | Reforested riparian buffers provide flood benefits by protecting adjoining properties from flood debris. | This project is performed in two venues. 1. The lead entity coordinators for salmon recovery supports projects for SRFB funding to enhance riparian buffers. 2. During the SMP update the County will need to develop shoreline restoration plans. | 2 | 22-23 |  |  | Additional data from Mark Swartout 3/27/12
115 | Biostabilization (bank stabilization with riparian vegetation |  | Structural |  |  |  |  | 1,4 | 22-23 | Moved from Bank Protection
116 | Galvin Road area; downstream Grand Mound - Oxbow reconnection |  | Structural |  |  |  |  | 13 | 24 | Moved from Conveyance Capacity
117 | Oakville backwater - Oxbow reconnection |  | Structural | Chehalis Mainstem Management Unit |  |  |  | 13 | 24 | Moved from Conveyance Capacity
118 | Porter area - Oxbow reconnection |  | Structural | Chehalis Mainstem Management Unit |  |  |  | 13 | 24 | Moved from Conveyance Capacity
119 | State Route 6 oxbow - Oxbow reconnection |  | Structural | Chehalis Mainstem Management Unit |  |  |  | 13 | 24 | Moved from Conveyance Capacity
120 | Horseshoe Lake oxbow - Oxbow reconnection |  | Structural | Chehalis Mainstem Management Unit |  |  |  | 13 | 24 | Moved from Conveyance Capacity
121 | Pheasant Farm Fords Prairie - High flow side channels |  | Structural | Chehalis Mainstem Management Unit |  |  |  | 13 | 24 | Moved from Conveyance Capacity
122 | Dillenbaugh Creek - Oxbow reconnection |  | Structural | Newaukum Management Unit |  |  |  | 13 | 24 | Moved from Conveyance Capacity
123 | Salzer Creek - Oxbow reconnection |  | Structural | Newaukum Management Unit |  |  |  | 13 | 24 | Moved from Conveyance Capacity
124 | Salzer Creek - Oxbow reconnection; wetland connection |  | Structural | Newaukum Management Unit |  |  |  | 13 | 24 | Moved from Conveyance Capacity
125 | Riparian habitat inventory |  | Non-structural | Basin-wide |  |  |  | 1,4 | 22-23 | Moved from Planning
126 | Develop a floodplain property acquisition program |  | Non-structural | Basin-wide |  |  |  | 1,4 | 22-23 | Moved from Planning
127 | Open old migration channels to allow river braiding |  | Structural | Wynoochee and Satsop Rivers |  |  |  | 1,4 | 22
128 | Correct barrier culverts - improve fish passage:
i | Porter Creek correct barrier culverts |  | Structural | Black Management Unit |  |  |  | 13 | 23 | Move from floodplain protection
ii | Albert-Demsey Creek Tributary R7 correct barrier culverts |  | Structural | Black Management Unit |  |  |  | 13 | 23 | Move from floodplain protection
iii | Baker-Goliath Creek correct barrier culvert |  | Structural | Black Management Unit |  |  |  | 13 | 23 | Move from floodplain protection
iv | Bailey Fish Barrier correct barrier culvert |  | Structural | Black Management Unit |  |  |  | 13 | 23 | Move from floodplain protection
v | Cedar Creek Road - correct barrier culvert |  | Structural | Black Management Unit |  |  |  | 13 | 23 | Move from floodplain protection
vi | Tilley Road - replace barrier culvert |  | Structural | Black Management Unit |  |  |  | 13 | 23 | Move from floodplain protection
vii | Upper Chehalis River - |  | Structural | Boistfort Management Unit |  |  |  | 13 | 24 | Move from floodplain protection
viii | South Fork Chehalis - |  | Structural | Boistfort Management Unit |  |  |  | 13 | 24 | Move from floodplain protection
ix | Stillman Creek - correct barrier culverts |  | Structural | Boistfort Management Unit |  |  |  | 13 | 24 | Move from floodplain protection
x | Lincoln Creek - Correct barrier culverts |  | Structural | Boistfort Management Unit |  |  |  | 13 | 24 | Move from floodplain protection
xi | Independence Creek - Correct barrier culverts |  | Structural | Boistfort Management Unit |  |  |  | 13 | 24 | Move from floodplain protection
xii | Garrard Creek (county and private properties) - Correct barrier culverts |  | Structural | Boistfort Management Unit |  |  |  | 13 | 24 | Move from floodplain protection
xiii | Gaddis Creek - Correct barrier culverts |  | Structural | Lincoln Management Unit |  |  |  | 13 | 24 | Move from floodplain protection
xiv | Rock/Williams Creek - Correct barrier culverts |  | Structural | Lincoln Management Unit |  |  |  | 13 | 24 | Move from floodplain protection
xv | Bunker Creek - Correct barrier culverts |  | Structural | Lincoln Management Unit |  |  |  | 13 | 24 | Move from floodplain protection
xvi | Scammon, Mill, and Stearns Creeks - Correct barrier culverts |  | Structural | Lincoln Management Unit |  |  |  | 13 | 24 | Move from floodplain protection
xvii | Wolf-Davis Creek R6 -Correct barrier culverts |  | Structural | Lincoln Management Unit |  |  |  | 13 | 24 | Move from floodplain protection
xviii | Harris Creek Fish Enhancement - No other information provided |  | Structural | Lincoln Management Unit |  |  |  | 13 | 24 | Move from floodplain protection
xix | Harris Creek - Correct barrier culverts |  | Structural | Lincoln Management Unit |  |  |  | 13 | 24 | Move from floodplain protection
xx | North Fork Newaukum - Correct barrier culverts |  | Structural | Newaukum Management Unit |  |  |  | 13 | 24 | Move from floodplain protection
xxi | Middle Fork Newaukum - Correct barrier culverts |  | Structural | Newaukum Management Unit |  |  |  | 13 | 24 | Move from floodplain protection
xxii | Salzer Creek - Correct barrier culverts |  | Structural | Newaukum Management Unit |  |  |  | 13 | 24 | Move from floodplain protection
xxiii | Dillenbaugh Creek - Correct barrier culverts |  | Structural | Newaukum Management Unit |  |  |  | 13 | 24 | Move from floodplain protection
xxiv | Berwick Creek - Correct barrier culverts |  | Structural | Newaukum Management Unit |  |  |  | 13 | 24 | Move from floodplain protection
xxv | Lucas Creek - Replace culvert |  | Structural | Newaukum Management Unit |  |  |  | 13 | 24 | Move from floodplain protection
xxvi | Lucas Creek - Replace culvert |  | Structural | Newaukum Management Unit |  |  |  | 13 | 24 | Move from floodplain protection
xxvii | Skookumchuck River - Correct barrier culverts |  | Structural | Skookumchuck Management Unit |  |  |  | 13 | 24 | Move from floodplain protection
xxviii | Skookumchuck River - Twin culverts under Main St. at 11th |  | Structural | Skookumchuck Management Unit |  |  |  | 13 | 24 | Move from floodplain protection | Repetitive with xxxii - Suggest remove
xxix | Culvert projects on Hiram Hall Road |  | Structural | Grays Harbor County |  |  |  | 1,4 | 22
xxx | Install culverts under South Bank River Road along approach to Sickman-Ford Bridge |  | Structural | Chehalis Reservation |  |  |  | 3 | 22 | CTIR in cooperation with Grays Harbor and Watershed Co-op- No assistance from Flood Authority | Tribe is doing a hydraulic analyses and is seeking funding.
xxxi | Install large-diameter culverts beneath State Road at Harris Creek |  | Structural | Reservation |  |  |  | 3 | 22 | CTIR in cooperation with Grays Harbor- No assistance from Flood Authority | Project to be completed in 2012
xxxii | Twin culverts under Main Street at 11th |  | Structural | Bucoda - Main Street | Not determined | Prevents water from backing up causing localized flooding due to the elevation of Main St. | Need design to detemine precise flood benefits and cost estimates. | 1,4 | 23 | Greg will check with Mark S. - keep on list. Not started due to lack of funds
xxxiii | Relief culvert for north side runoff |  | Structural | Oakville |  |  |  | 1,4 | 23 | Dan T. - leave in - included in the cities Flood Hazard Mitigation Plan | Dan T. - leave in - included in the cities Flood Hazard Mitigation Plan
PROGRAMMATIC SOLUTIONS
129 | Continue enforcement of existing land use regulations and permitting processes |  | Non-structural | Grays Harbor County |  |  |  | 9 | 22
130 | Revise shoreline regulations to encourage ‘shoreline protective structures” to be “bioengineered”. |  | Non-structural | Thurston County | Ecology grant. The in-house costs are estimated to be $500,000. This estimate is included in project #114 above. | Provides additional floodplain storage and can often be more stable than hard shoreline structures. | The update of the SMP will restart toward the end of 2012 after the Critical Areas Ordinance is adopted. It’s estimated to end in 2015. | 6 | 23 |  |  | Additional data from Mark Swartout 3/27/12
131 | Floodplain conservation easement program |  | Non-structural | Basin-wide |  |  |  | 1,4 | 22-23
132 | Improve floodplain regulations |  | Non-structural | Basin-wide |  |  |  | 1,4 | 22-23
133 | Tax breaks for removing structures from floodplain |  | Non-structural | Basin-wide |  |  |  | 1,4 | 22-23
134 | Penalization for building in the floodplain |  | Non-structural | Basin-wide |  |  |  | 1,4 | 22-23
135 | Reevaluate land uses and zoning based on new mapping |  | Non-structural | Basin-wide |  |  |  | 1,4 | 22-23
136 | Improve floodplain and stormwater regulations |  | Non-structural | Centralia |  |  |  | 2 | 22-23
137 | Join the NFIP Community Rating System |  | Structural | Basin-wide |  |  |  | 1,4 | 22-23 | Moved from Reduction of Damage
138 | Form a governance body for flood planning |  | Non-structural | Basin-wide |  |  |  | 1,4 | 22-23 | Moved from Governance and Management