## 1. Local Projects 11-17-2022
Proposed Local Projects Framework
Question -- Does the Flood Authority support the direction of this proposed 2023-25 Local Projects Framework?
Category | Sponsors (11) | Projects (29) | 2019-21 |  | 2021-23 |  |  | 2023-25 |  |  | Comments
|  |  | CBB Funded (5-05-2022) | CBB Funded (7-07-2022) | FA Summary (3-17-2022) | CBB Funded (7-07-2022) | OCB Funded (10-11-2022) | Remaining "Need" | Proposed "Framework" | Near-term (2023/24); Mid-term (2024/25); Longer-term (2025/26)
Demolition | Chehalis | Derelict WWTP Demolition and Removal | [5 empty] | 4962977 | 250000 | Longer-term | Refine cost; Fund permitting phase first (to get "shovel ready"); Evaluate fill.
Erosion | GHCD | Cloquallam Creek Erosion Management Pilot Project |  |  | 112499
| GHCD | Lower Satsop Right Bank Conservation (Design) |  |  | 120795 |  | 75000
| GHCD | Lower Satsop Right Bank Conservation (Construct) |  |  | 1681140 |  |  | 1673193 | 0 | n/a | Fund through ASRP or OCB erosion/integrated.
| GHCD | Hoquiam RV Park (Design) |  |  | 19317 |  |  |  | 19317 | Near-term | Reprogram (2021-23 staff support); Fund again 2023-25.
| Port of Grays Harbor | Haul Road Emergency Project (Short-Term) | 125000 |  |  | 400000
| Port of Grays Harbor | Haul Road Mid-Term Project |  |  |  |  | 170000 | 1620000 | 0 | n/a | Fund through OCB erosion/integrated.
Farm Pad | Lewis CD | Osborn/Brunoff Livestock, Equipment Pad | [5 empty] | 160000 | 160000 | Near-term | Fund
Flood Reduction | Aberdeen | Fry Creek Restoration and Flood Reduction Design |  |  | 145000
| Centralia | China Creek Flood Storage and Fish Habitat Restoration Project (Phases 1-4) |  |  |  | 643000 |  | 200000 | 200000 | Longer-term | Fund
| Port of Chehalis | Berwick Creek Flood Reduction and Restoration |  |  | 10743 | 89257
Flood Warning System | Lewis County | Basin Gage Plan Update (Chehalis River Basin Flood Authority) |  | 75000
| Lewis County | New China Creek Gage (Chehalis River Basin Flood Authority) |  |  |  | 35000
Infrastructure Protection | Montesano | Montesano Water Supply Resiliency | [5 empty] | 350000 | 350000 | Near-term | Fund
Levee | Aberdeen | Southside Levee Recertification
Pump Station | Aberdeen | Division Street |  |  |  |  | 500000 |  |  |  | Address future cost and schedule via Joint Surface Water Management Plan.
| Aberdeen | Farragut Street |  |  | 464518 |  | 654000 | 8346000 | 7302750 | Near-term or Mid-term | Refine cost. Should reduce by 10-15% (mid- to late-December).
| Hoquiam | 10th Street |  |  | 334750 |  | 300000 | 3300000 | 3300000 | Near-term or Mid-term | Refine cost.
| Hoquiam | K Street |  |  |  |  | 350000 |  |  |  | Address future cost and schedule via Joint Surface Water Management Plan.
| Hoquiam | Queen Ave |  |  | 295200 |  | 300000 | 2400000 | 2400000 | Near-term or Mid-term | Refine cost.
Roadmap | Chehalis | Flood Storage and Habitat Enhancement Master Plan
| Cosmopolis | Joint Surface Water Management Comprehensive Plan |  |  |  |  | 400000
| Cosmopolis | Mill Creek Multi-Objective Implementation Plan, Phase 2 |  |  | 145000 | 25000
| GHCD | Chehalis (RM 13-20) Erosion Analysis/Roadmap | 60000 | 150000
| Port of Chehalis | Regionalized Floodwater Management Approach |  |  | 353636
Study | Lewis County | S.F. Chehalis /Boistfort CMZ |  |  | 59100 |  |  |  | 59100 | Near-term | Reprogram (2021-23 staff support); Fund again 2023-25.
| Montesano | Montesano Flood Mitigation Study (Phase 1) | [5 empty] | 120000 | 120000 | Longer-term | Fund
| Montesano | WWTP Bank Stabilization Project Impacts Analysis | [5 empty] | 90000 | 90000 | Longer-term | Fund
| Port of Chehalis | Chehalis Industrial Park Hydraulic Modelling |  |  | 84985
Other | Lewis County | Fiscal Agent, Staff Support |  |  | 193295 |  |  | 291000 | 291000 | Near-term | Fund
| RCO | 1.5% |  |  | 60299.67 | 17883.855 | 41235 | 352697.55 | 218132.505 | Near-term | Fund
|  |  | 185000 | 225000 | 4080277.67 | 1210140.855 | 2790235 | 23865867.55 | 14760299.505
|  |  | 410000 |  | 8080653.525 |  |  | 23865867.55 | 14760299.505
TABLE 1
|  | 2019-23 Expenditures = 18 Planning Projects + 2 "Other" (51%) --> | 4250757.525
|  | 2019-23 Expenditures = 10 Construction projects (49%) --> | 4239896
TABLE 2
|  | Initial 2023-25 Request --> | 25971170
|  | Remaining 2023-25 "Need" --> | 23865867.55
|  | Proposed Framework Approach --> | 14760299.505
|  | 2023-25 Expenditures = 6 Planning Projects + 2 "Other" (9%) --> | 1247549.505
|  | 2023-25 Expenditures = 5 Construction projects (91%) --> | 13512750
TABLE 3
|  | 2012-13 | 5000000 | 5000000
|  | 2013-15 | 10700000 | 10700000
|  | 2015-17 | 15700000 | 15700000
|  | 2017-19 | 9600000 | 9600000
|  | 2019-21 (added $410,000) | 6710000 | 6300000
|  | 2021-23 (added $8,080,654) | 12130654 | 4050000
|  | 2023-25 |  | 14760299.505
|  | Total --> | 59840654 | 66110299.505
|  | Average (5.5 biennia) --> | 10880118.9091 | 12020054.4555

## 2. Pumps Assessed Value
Project | City | Activity | Tributary Upstream Basin (Acres) | Highest Point In Basin Above Sea Level (ft.) | Lowest Point In Basin Above Sea Level (ft.) | No. of Parcels | Assessed Value (2022 Dollars) | Critical Facilities Requring Protection in this Basin
Queen Avenue PS | Hoquiam | Construct | 95 | 255 | 10 | 221 | 27885875 | Lincoln Elementary School
10th Street PS | Hoquiam | Construct | 51 | 160 | 10 | 78 | 25060708 | Hoquiam Police Station, Hoquiam City Hall, Hoquiam Fire Department
Farragut Street PS | Aberdeen | Construct | 322 |  |  | 529 | 72375623 | Miller Junior High School
SUB-TOTAL --> | [5 empty] | 828 | 125322206
K Street PS | Hoquiam | Design (PS&E) | 160 | 20 | 10 | 518 | 89213037
Division Street PS | Aberdeen | Design (PS&E) | 245 | 345 | 10 | 1241 | 208036273 | AJ West Elementary School; Harbor High School; Sea Mar Medical Clinc; Fresenius Dialysis Center
Division Street PS -- Lincoln | Aberdeen | Design (PS&E) -- Divert to Division | 46 | 15 | 10 | 341 | 41473223 | Aberdeen PW Facility, Cascade Natural Gas Field Office,
Division Street PS -- Washington | Aberdeen | Design (PS&E) -- Divert to Division | 192 | 345 | 10 | 732 | 160416203 | Quinault Indian Nation Wellness Center, McDermoth Elementary School, NMFS local office, Labor & Industries Local Office
SUB-TOTAL --> | [5 empty] | 2832 | 499138736
TOTAL --> | [5 empty] | 3660 | 624460942