## Technical Comparison
EFDC vs. SSM (Technical Comparison)
| King County EFDC Model | QEA EFDC-SEDZLJ Model | Dynamic Solution Version EFDC | PNNL SSM-Toxi (or FVCOM-Toxi) Model
Model Scope | Hydrodynamic (Turbulence, Salinity), Temperature model can be set up | Hydrodynamic (Turbulence, Salinity), Temperature model can be set up | Hydrodynamic | Hydrodynamic (Turbulence, Salinity, & Temperature, Heatfluxes)
| Sediment Transport (with Conventional Formulations) | Sediment Transport (Formulations and Sedflume Data) | Sediment transport | Sediment Transport (Conventional Formulations)
| Total PCBs, can be used to simulate other pollutants |  | Toxic fate and transport | Total PCBs (by 9/30/20) (EPA Support)
|  |  | Water quality | Metals and PAHs by (9/20/21) (With Ecology Support)
Modeling Framework | EFDC Hydrodynamic | EFDC Hydrodynamic | EFDC Hydrodynamic | FVCOM Hydrodynamics
| with internally direct linked Sediment Transport | with indirect linked Sediment Transport ((EFDC + SEDZLJ) | with internally direct linked Sediment Transport | with internally direct linked Sediment Transport
| with internally direct linked Toxic Fate and Transport | Need Linkage for Toxic Fate and Transport | with internally direct linked Toxic Fate and Transport | Externally coupled toxics fate and transport (9/30/20)
| with internally direct linked water quality | Need Linkage for Water Quality | with internally direct linked water quality | with internally direct linked water quality (calibrated)
| No Wind-wave sub-model | No Wind-wave sub-model | No Wind-wave sub-model | Could add wind-wave sub-model if needed
Code Availability | Yes, updated code from EPA is preferred | Yes | Yes, if purchase | Yes
Grid | 521 Horizontal Cells | 1312 Horizontal Cells | can be generated to meet the requirement based on previous grid | SSM Grid - (25k horizontal cells)
| 58 x 62 | 23 x 389 |  | Potential High Resolution Dowamish Grid (40k)
| GEFDC grid generation |  |  | 10-20 m horizonal resolution
| VEFDC or Dynamic Solutions grid generator will be used for grid re-generation | VEFDC or Dynamic Solutions grid generator will be used for grid re-generation | VEFDC or Dynamic Solutions grid generator will be used for grid re-generation
| (can be adjusted and improved) | (can be adjusted and improved) |  | Grid generation using SMS software
Number of Water Column Layers | 10 (can be modified) | 10 (can be modified) | can be specified to meet the requirement | 10
Drying and Wetting | Yes | Yes | Yes | Yes
Number of Sediment Bed Layers | 4 (for sediment transport and toxic simulation), can be modified | 5 (for sediment transport simulation), can be modified | can be specified to meet the requirement | 2
Sediment Classes | 3 (2 Cohesives + 1 Noncohesive) | 4 (2 Cohesives + 2 Noncohesives) |  | 3 (1 Cohesives + 2 Noncohesive) (Planned & TBD)
| Clay (1 - 4 µm): 1.0×10-10 m/s | Clay and Fine Silt (< 10 µm): D50 = 5 µm |  | Clay (1 - 4 µm): 1.0×10-10 m/s
| Silt (4 - 62 µm): 2.0×10-4 m/s | Medium and Coarse Silt (10 - 62 µm): D50 = 20 µm |  | Silt (4 - 62 µm): 2.0×10-4 m/s
| Sand (62 - 500 µm): 0.04 m/s | Fine Sand (62 - 250 µm): D50 = 130 µm |  | Sand (62 - 500 µm): 0.04 m/s
Medium and Coarse Sand (250 - 2,000 µm): D50 = 540 µm
| can be modified and specified to meet the requirement | can be modified and specified to meet the requirement | can be specified to meet the requirement
Bedload | Not Simulated, but can be activated and simulated based on analysis | Simulated for medium and coarse sand, can be modified based on analysis | can be activated and simulated | Simulated for silt and sand
Simulation Period | 2005 - 2006 (hot-started) | 1960 - 1989 (30 years) |  | TBD (based on Ecology Needs)
|  | Hydrodynamic model: 7 days spin-up for each year |  | Hydrodynamic model: Spinup depends on whether Duwamish Model
|  | Sediment Transport model: hotstarted for each year |  | is standalone or operated embedded within SSM
Sediment Transport model: hotstarted for each year
| can be extended to multiple years | can be extened to meet the requirement | according to the requirement
Computational Time | ~6 hours for 1 year simulation | ~12 hours for 1-year hydrodynamic simulation | N/A, refer to King County and QEA model for initial estimate | A function of grid size and resolution
|  | > 4 hours for 1-year sediment transport simulation |  | 24 to 48 hrs for 1 year (for 20 m high resolution grid size)
Parallelized Code operated on PNNL Cluster
Grid Generator Availability | Yes, GEFDC | No | Yes, Dynamic Solution grid generator (CVLGrid) or VEFDC | No
Post-processor Availability | Yes | No | Yes, EFDC Explorer if purchase | No - PNNL uses a combination of Matlab and Fortran
to conduct Post Processing

## Remaining Work
EFDC vs. SSM (Remaining Work)
| King County EFDC | QEA EFDC-SEDZLJ Model | Dynamic Solution EFDC | PNNL SSM-Toxi (or FVCOM-Toxi) Model
Grid re-generation | QEA's original EFDC grid generation files is needed. The combination of King County and QEA LDW grid is expected for the eventual EFDC modeling, plus possible cell modification and grid extension to the upstream boundary at Kent. | QEA's original EFDC grid generation files is needed. The combination of King County and QEA LDW grid is expected for the eventual EFDC modeling, plus possible cell modification and grid extension to the upstream boundary at Kent. | QEA's original EFDC grid generation files is needed. The combination of King County and QEA LDW grid is expected for the eventual EFDC modeling, plus possible cell modification and grid extension to the upstream boundary at Kent. | Current SSM mesh needs to be narrowed down to the LDW area, and then the resolution of LDW mesh needs to be increased.
Sediment Transport module development | Sediment Transport (with Conventional Formulations). However, latest EPA/Tetra Tech version EFDC probably has the SEDZLJ sediment transport model. | SEDZLJ sediment transport model, which is used in LDW superfund STM modeling. | Both traditional EFDC Sediment Transport model (with Conventional Formulations) and SEDZLJ sediment transport model are available. We can choose either one. | Sediment Transport (with Conventional Formulations). The sediment transport model needs to be linked with SSM-Toxi.
Toxic Fate and Transport model development | Available (EFDC Toxic) | No, TBD | Available (EFDC Toxic) | No. EPA is funding the PCB module, PLA will still require toxic modules for PAH and metals.
Water Quality Module development | Available. Needs calibration. | No. Needs linkage. | Available. Needs calibration. | Available and it is already calibrated.
Water quality module template input files | No, need to request (associated with the updated EPA/Tetra Tech version EFDC code). | No | Yes | Yes

## Resources Required
EFDC vs. SSM (Resources Required)
|  | King County EFDC | QEA EFDC-SEDZLJ Model | Dynamic Solution EFDC | PNNL SSM-Toxi (or FVCOM-Toxi) Model
Project Management | Approximate work required | Total work required is around 7,300 hrs. No outside contractor required. | Total work required is around 7,600 hrs. Outside consulting time required estimated to be ~1,000 hrs for linkage development (to generate the sediment transport and organic carbon linkage files for toxic module) + 1,000 hrs for model review + meeting + document. | Total work required is around 7,300 hrs. No outside contractor required. | Most of the code development will be done by PNNL. Ecology modeler will be responsible for model inputs, calibration and running scenarios. So it is less work for Ecology's modelers' team. The work for PNNL will be done in two phases. Phase I: (Year 1) SSM Refinement for Duwamish Hydrodynamic Model Setup and validation. (Year 2) Incorporation of Toxics Kinetics into FVCOM-ICM-Metals, PAHs and DEHP. Phase II: include (a) Additional model refinement driven by project needs, and (b) Sediment transport calibration, and (c) multiple class sediment flux and bedload incorporation into toxics kinetics calculations from hydrodynamics.
| Project Time | In-house. Model post-processing time is significant and unpredictable extra hours will be required to visualize the modeling results. It might take more three years. | Estimated to be three year FTE plus consulting time. It can happen in the same three year timeframe. No post-processor is available. Model post-processing time is very significant and unpredictable extra hours will be required to visualize the modeling results. | In-house. Because it comes with a nice post processor, it can minimize post processor time. The total project time estimated to be three years with outside technical support. | Assuming Ecology WQ is the only funding source (200k per two years), It could take 4-6 years. It has a nice post-processor that can minimize post processor time.
| Staff Training | Ecology modelers and King County modelers are familiar with the EFDC model | Ecology modelers and King County modelers are familiar with the EFDC model | Ecology modelers and King County modelers are familiar with the EFDC model | Ecology EAP staff are familiar with SSM. Ecology WQ modeler will need training.
| QA/QC | Staff in Ecology and outside consultants are familiar with EFDC to review the modeling files. | Staff in Ecology and outside consultants are familiar with EFDC to review the modeling files. | Staff in Ecology and outside consultants are familiar with EFDC to review the modeling files. | Fewer staff/outside contractors are familiar with the SSM to review the modeling files.
Cost | Funding Required | In-house. No cost required. The remaining funds can be applied to outside technical support. | Estimated to be around 400k (Assuming $200/hr for consulting fee) | In-house work. 5k/year/user or 15k/multiple users or 55k/lifetime/user for software purchase. The remaining funds can be applied to outside technical support. | Estimated to be around 400k -600k (Phase I: 200k, Phase II: 200k - 400k depends on the progress)
| Cloud Services Fee | no | no | no | Required, varying from 4.5k to 13.5k per year.
| Contracting mechanism and timeframe | In-house | Outside contract could take up to one year for the contracting process | In-house. May require outside contractor for technical support | Interagency agreement can be signed in couple weeks.
Future application |  | LDW for now, could be extended later | LDW for now, could be extended later | LDW for now, could be extended later | Could spin-off to potential study areas
Contingency |  | Most work will be in house. The risk will be if we lose key staff, we will need to re-hire modelers. | Require hiring of outside consultants to bomplete code development. If we can not find right consultant or the cost is too high, there is risk that the project will be delayed. | Most work will be in house. The risk will be if we lose key staff, we will need to re-hire modelers. | If the contract is delayed due to any uncertainty, the project will be delayed.