## committee Project Schedule
Project Elements & Schedule for Advisory Committee
Task | Due Dates | Committee Effort
Literature Research | 2017-12-31
With help from the working group, we will identify literature on the effectiveness and barriers to LID. |  | Committee to provide input during meetings and to Linda Bentley for collating and uploading to project website.
Identify Target Audience | 2018-01-31
With help from the working group, we will identify the types of local government officials, developers and others involved in the development process who could implement those practices. |  | Committee to provide input during meetings or directly to Charlene Andrade for collating and transmitting to Consultant.
Research & Reporting: Consultant Hired | 2018-02-28
Meetings in Support of Consultant & Research Process. |  | Committee may be asked to provide input to consultnt during a few meetings and responding to discrete requests from project team on coordination, collaboration, advising, and review of documents.
Summary of Best LID Practices | 2018-03-31
With help from the working group and the literature search findings, we will identify best LID practices to promote to local government, developers and others involved in the development process. |  | Committee to provide input during meetings and to Linda Bentley for collating and uploading to project website.
Draft Social Marketing Report & Draft Guidance | 2018-08-31
The social marketing consultant we hire will develop a social marketing report on barriers and motivations/benefits to developers to incorporate LID into their projects and draft guidance based on the report. |  | Committee to review reports and guidance and provide comments. Committee may be asked (if members are amenable) to also provide input during a few meetings and responding to discrete requests from project team. May include review of status, methods, results.
Final Social Marketing Report & Draft Guidance | 2019-03-30
We will convene the work group to review the draft social marketing report and the draft guidance and provide comments to the consultant. The consultant will prepare a final report identifying barriers and motivations/benefits to developers to incorporating LID into urban center projects. The consultant will produce final guidance based on the final report. |  | Committee to review reports and guidance and provide comments. Committee may be asked (if members are amenable) to also provide input during a few meetings and responding to discrete requests from project team. May include review of status, methods, results.